## ProjectSchedule
Game Algorithm Assignment
Space Battle
|  | Project Start: | 2020-08-01
|  | Display Week: | 1 |  |  | 2020-08-01 | [6 empty] | 2020-08-08 | [6 empty] | 2020-08-15 | [6 empty] | 2020-08-22 | [6 empty] | 2020-08-29 | [6 empty] | 2020-09-05 | [6 empty] | 2020-09-12 | [6 empty] | 2020-09-19 | [6 empty] | 2020-09-26 | [6 empty] | 2020-10-03
 | time axis 2020-08-01 to 2020-10-09
TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2020-08-01 to 2020-10-09
Game Proposal
Brainstorm with members | Michelle & Fang Jee | 100% | 2020-08-01 | 2020-08-05 | 5 | bar: 2020-08-01
Draft the proposal | Michelle & Fang Jee | 100% | 2020-08-03 | 2020-08-05 | 3
Prepare presentation slides | Michelle & Fang Jee | 100% | 2020-08-04 | 2020-08-05 | 2
Presentation for lecturer's approval | Michelle & Fang Jee | 100% | 2020-08-06 | 2020-08-06 | 1
Milestone 1
Coding
Add Player | Michelle | 100% | 2020-08-10 | 2020-08-11 | 2
Add Enemy | Michelle | 100% | 2020-08-10 | 2020-08-11 | 2
Add Collision | Fang Jee | 100% | 2020-08-10 | 2020-08-12 | 3
Add Bullet | Michelle & Fang Jee | 100% | 2020-08-10 | 2020-08-12 | 3
Add Main Menu | Fang Jee | 100% | 2020-08-13 | 2020-08-15 | 3
Add Asteroids | Michelle | 100% | 2020-08-13 | 2020-08-15 | 3
Draft milestone report | Michelle | 100% | 2020-08-14 | 2020-08-19 | 6
Fix bugs | Michelle & Fang Jee | 100% | 2020-08-17 | 2020-08-19
Project Demo | Michelle & Fang Jee | 100% | 2020-08-20 | 2020-08-20 | 1
Milestone 2
Level design | Michelle & Fang Jee | 0% | 2020-08-21 | 2020-09-03 | 14
Coding
Add Boss | Fang Jee | 50% | 2020-08-21 | 2020-08-24 | 4
Add Turret | Michelle | 100% | 2020-08-21 | 2020-08-24 | 4
Add Enemy2 | Michelle | 50% | 2020-08-25 | 2020-08-29 | 5
Add Missile | Fang Jee | 50% | 2020-08-25 | 2020-08-29 | 5
Add GUI | Michelle | 0% | 2020-08-30 | 2020-09-03 | 5
Add sound effects | Fang Jee | 0% | 2020-08-30 | 2020-09-03 | 5
Code Level | Fang Jee | 0% | 2020-09-04 | 2020-09-06 | 3
Draft milestone report | Michelle | 100% | 2020-09-04 | 2020-09-09 | 6
Fix bugs | Michelle & Fang Jee | 100% | 2020-09-07 | 2020-09-09 | 3
Project Demo | Michelle & Fang Jee | 0% | 2020-09-10 | 2020-09-10 | 1
Finalization
Final coding | Michelle & Fang Jee | 0% | 2020-09-11 | 2020-09-20 | 10
Conduct beta testing | Michelle | 0% | 2020-09-21 | 2020-09-26 | 6
Fix identified bugs | Michelle & Fang Jee | 0% | 2020-09-27 | 2020-09-30 | 4
Draft final report | Michelle & Fang Jee | 0% | 2020-10-01 | 2020-10-07 | 7
Prepare presentation slides | Michelle & Fang Jee | 0% | 2020-10-05 | 2020-10-07 | 3
Submit final program | Fang Jee | 0% | 2020-10-07 | 2020-10-07 | 1
Game Demo | Michelle & Fang Jee | 0% | 2020-10-08 | 2020-10-08 | 1
Note on H6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.